## Timetable
[INSERT TITLE]
Key Details | Date | Key Details |  | Name(s)
Policy brief Summarised | [date]
Policy brief Circulated | [date]
Activities | Checklist | Responsible person | Due | Follow-up Action
1. Brainstorm session | Working Group, one-on-one, other
2. Scanning for supporting evidence | Survey international/ national agreements/ legislation; similar reports; background material; potential interviewees
3. Design Phase
The lead writer is responsible and accountable for the final product's content. | Compliance with policy brief guidelines: summary provided to all writers |  | 20 April
| Conference call on policy brief tasks with team members; identify peer-reviewers |  | 24 April
| Action Plan - draft |  | 26 April
| Working Group members write sections |  | 26 April
4. Proposal: full draft
| Full draft Narrative |  | 4 May
| Full draft Narrative and annexes to peer review group |  | 4 May | Returned by 8 May
| Lead autor inputs suggested changes |  | 8 May
5. Proposal Finalised
| Second conference call on policy brief final draft | Working Group | 8 May, AM
| Review - : evaluate strength of narrative to guideline language; compliance | Programme team | 8 May, PM
| Working Group final compliance check list (gaps/problems) created and shared with advisor, other writers and | Working Group | 8 May, PM
| Review Narrative | Lead Writer | 9 May, AM
| Website copy edit | Website editor | 9 May, PM
| Authorised sign-off | Key Expert 3 | 10 May
6. Submission
The Programme Team in Kyiv are responsible for compiling the final documents. The Country Coordinator and Working Group are responsible for sending them to relevant target groups. | Submission: as required and agreed /discussion about final steps | Programme Team/ Country Coordinator/ Working Group | 11 May | Actual deadline is 14 May
| Follow-up confirmation | Liaison Officer | 15 May